## Sheet1
PHASE DATES AND BUDGET HOURS
Audit Plan Title | Assignment Name | Assignment Code | Type | Owner | Phase | Milestone | Actual Start | Actual End | Actual Hours | Phase 1 - Phase Estimated End Date | Phase 1 - Phase Actual End Date | Phase 1 - Phase Estimated Hours | Phase 2 - Phase Estimated End Date | Phase 2 - Phase Actual End Date | Phase 2 - Phase Estimated Hours | Phase 3 - Phase Estimated End Date | Phase 3 - Phase Actual End Date | Phase 3 - Phase Estimated Hours | Phase 4 - Phase Estimated End Date | Phase 4 - Phase Actual End Date | Phase 4 - Phase Estimated Hours | Phase 5 - Phase Estimated End Date | Phase 5 - Phase Actual End Date | Phase 5 - Phase Estimated Hours | DataSourceID | ProjectID | AuditPlanID
2021 Audit Plan | IOS/2020/hp/Memo.088-Memo on Fraud Risk Assessment of the Field Network | 2020-HQ-Memo Fraud Risk Assessment | Memorandum | Flora Moutard; Hir Purkait | 4-Finalization of Workpapers |  | 2020-06-02 | 2020-08-04 | 154.5 | 2020-06-05 | 2020-06-30 |  | 2020-06-30 | 2020-07-31 |  | 2020-07-15 | 2020-08-04 |  | 2020-10-04 | 2021-07-19 |  |  |  |  | 1 | 137 | 5
2021 Audit Plan | IOS/AUD/2021/03-Audit of UNESCO's Office in Juba | 2020-FO-JUB | Field Audit | Refiloe Ethan Mohapi; Sameer Pise; Shashank Shekhar | 5-Follow-up of recommendations | Start follow-up | 2020-10-08 | 2021-03-29 | 984.5 |  | 2020-12-18 |  |  | 2021-03-01 |  |  | 2021-03-29 |  |  | 2021-07-28 |  |  |  |  | 1 | 146 | 5
2021 Audit Plan | IOS/AUD/2021/06-Audit of UNESCO's Office in Mexico City | 2020-FO-MXC | Field Audit | Hir Purkait | 5-Follow-up of recommendations | Start follow-up | 2020-09-15 | 2021-06-28 | 1468.25 |  | 2020-11-13 |  |  | 2021-03-15 |  |  | 2021-06-28 |  |  | 2021-10-05 |  |  |  |  | 1 | 147 | 5
2021 Audit Plan | IOS/AUD/2021/05-Audit of UNESCO's Office in Dhaka | 2020-FO-DHA | Field Audit | Anastasia Beltyukova; Flora Moutard; Helen Thanassoulias | 5-Follow-up of recommendations | Start follow-up | 2021-01-29 | 2021-02-06 | 1344.3 |  | 2021-02-02 |  |  | 2021-03-15 |  |  | 2021-06-02 |  |  | 2021-06-14 |  |  | 2021-06-02 |  | 1 | 148 | 5
2021 Audit Plan | IOS/AUD/2021/04-Audit of UNESCO's Office in Kathmandu | 2020-FO-KAT | Field Audit | Flora Moutard; Tuyet-Mai Grabiel | 5-Follow-up of recommendations | Start follow-up | 2020-11-18 | 2021-05-10 | 698.3 |  | 2021-12-10 | 80 |  | 2021-02-26 | 320 |  | 2021-05-10 | 130 |  | 2021-05-31 |  |  |  |  | 1 | 149 | 5
2021 Audit Plan | Risk Assessment of CRM | 2020-IT-CRM | HQ Audit | Flora Moutard; Oyuna Tumurbaatar | 5-Follow-up of recommendations | Closure of the last recommendation | 2020-11-01 | 2020-12-15 | 207 |  | 2020-11-15 |  |  | 2020-12-15 |  |  | 2021-01-18 |  |  | 2022-04-27 |  |  |  |  | 1 | 151 | 5
2021 Audit Plan | IOS/AUD/2021/08-Audit of UNESCO's Environmental Management System | 2021-HQ-Environmental Sustainability | HQ Audit | Anastasia Beltyukova; Carles Soriano; Tuyet-Mai Grabiel | 5-Follow-up of recommendations | Start follow-up | 2021-02-02 | 2021-11-04 | 1106.7 |  | 2021-06-08 |  |  | 2021-06-08 |  |  | 2021-11-04 |  |  | 2021-11-22 |  |  | 2021-12-23 |  | 1 | 154 | 5
2021 Audit Plan | IOS/2021/cs/Memo.039-Advisory on Enterprise Risk Management | 2021-HQ-ERM | HQ Audit | Carles Soriano; Refiloe Ethan Mohapi | 5-Follow-up of recommendations | Closure of the last recommendation | 2021-03-01 | 2021-06-07 | 205 |  | 2021-07-19 |  |  | 2021-05-27 |  |  | 2021-06-07 |  |  | 2021-09-24 |  |  | 2021-09-24 |  | 1 | 155 | 5
2021 Audit Plan | IOS/AUD/2021/07-Audit of UNESCO's Recruitment | 2021-HQ-Recruitment | HQ Audit | Carles Soriano; Christian Muco; Flora Moutard; Hir Purkait | 5-Follow-up of recommendations | Start follow-up | 2020-12-14 | 2021-07-29 | 1054.25 |  | 2021-05-04 |  |  | 2021-06-22 |  |  | 2021-10-18 |  |  | 2021-10-19 |  |  |  |  | 1 | 156 | 5
2021 Audit Plan | IOS/EVS/PI198-Advisory of Sexual Exploitation and Abuse, Sexual Harassment | 2021-HQ-SEA&SH | Advisory Engagement | Alicia Alvarez-Gracia; Carles Soriano; Shashank Shekhar | 5-Follow-up of recommendations | Start follow-up | 2021-02-01 | 2021-07-31 | 349.5 |  | 2021-03-30 |  |  | 2021-06-25 |  |  | 2021-07-31 |  |  | 2021-08-01 |  |  | 2021-10-14 |  | 1 | 157 | 5
2021 Audit Plan | Vendor Creation on Internet Banking Tool (see FO Cross-cutting issues Assignment; kept for time tracking) | 2021-FO-Vendors & Bank |  | Christian Muco; Refiloe Ethan Mohapi | 2-Fieldwork | End of Fieldwork |  |  | 89.5 | [15 empty] | 1 | 158 | 5
2021 Audit Plan | IOS/AUD/2022/07-Performance Audit of Communication and Information Sector | 2021-HQ-CI | Performance Audit | Flora Moutard; Helen Thanassoulias; Refiloe Ethan Mohapi | 4-Finalization of Workpapers | Review Process | 2021-06-01 | 2022-05-24 | 1244.25 |  | 2021-09-29 |  |  | 2022-05-16 |  |  | 2022-05-24 | [7 empty] | 1 | 235 | 5
2021 Audit Plan | IOS/AUD/cs/Memo.073-Memo on Cross-cutting issues for Field Offices | 2021-FO-Crosscutting Issues | Memorandum | Anastasia Beltyukova; Carles Soriano; Christian Muco; Flora Moutard; Helen Thanassoulias; Hir Purkait; Refiloe Ethan Mohapi; Sameer Pise; Shashank Shekhar; Tuyet-Mai Grabiel | 5-Follow-up of recommendations | Closure of the last recommendation | 2021-04-01 | 2021-07-29 | 548.05 |  |  |  |  | 2021-07-15 |  |  | 2021-07-29 |  |  | 2022-04-06 |  |  |  |  | 1 | 236 | 5
2021 Audit Plan | IOS/AUD/2022/03-Audit of UNESCO's Implementation Partnership Agreements | 2021-HQ-IPAs | HQ Audit | Carles Soriano; Tuyet-Mai Grabiel | 5-Follow-up of recommendations | Start follow-up | 2021-09-01 | 2022-02-07 | 668 |  | 2021-10-12 |  |  | 2021-12-20 |  |  | 2022-03-07 |  |  | 2022-02-23 |  |  |  |  | 1 | 237 | 5
2021 Audit Plan | IOS/AUD/2022/02-Advisory on Organisation Culture | 2021-HQ-Organisation Culture | Advisory Engagement | Alicia Alvarez-Gracia; Flora Moutard; Hir Purkait | 5-Follow-up of recommendations | Closure of the last recommendation | 2021-06-29 | 2022-01-24 | 558 |  | 2021-09-17 |  |  | 2021-12-01 |  |  | 2022-01-24 |  |  | 2022-04-08 |  |  |  |  | 1 | 238 | 5
2021 Audit Plan | IOS/AUD/2021/09-Review of the Management Process for Diplomatic Status Requests Granted to Staff and Delegations | 2021-HQ-Diplomatic Status | HQ Audit | Anastasia Beltyukova; Sameer Pise | 5-Follow-up of recommendations | Start follow-up | 2021-06-24 | 2021-12-09 | 631.5 |  | 2021-10-11 |  |  | 2021-10-21 |  |  | 2021-12-09 |  |  | 2022-01-13 |  |  |  |  | 1 | 239 | 5
2021 Audit Plan | IOS/AUD/2022/01-SWIFT Community Standard Assessment | 2021-HQ-SWIFT | Advisory Engagement | Christian Muco; Refiloe Ethan Mohapi | 4-Finalization of Workpapers | Review Process | 2021-06-28 | 2022-01-21 | 200.5 |  | 2021-09-01 |  |  | 2021-11-30 |  |  | 2022-01-21 |  |  | 2022-02-04 |  |  | 2022-08-08 |  | 1 | 240 | 5
2021 Audit Plan | Advisory Engagement on Data Governance | 2021-IT-DataGovernance | IT Audit/Review | Christian Muco | 3-Reporting | Draft Report | 2021-09-01 |  | 706.75 |  | 2022-03-14 |  |  | 2022-04-06 |  |  | 2022-04-06 |  |  | 2022-04-06 |  |  |  |  | 1 | 241 | 5
2021 Audit Plan | IOS/AUD/2022/06-Performance audit of the World Heritage Centre | 2021-HQ-WHC | HQ Audit | Alicia Alvarez-Gracia; Carles Soriano; Hir Purkait; Thiago de Oliveira Teodoro | 4-Finalization of Workpapers | Review Process |  | 2022-04-22 | 725.75 |  | 2022-01-14 |  |  | 2022-04-01 |  |  | 2022-04-22 |  |  | 2022-05-06 |  |  |  |  | 1 | 242 | 5
2021 Audit Plan | IOS/AUD/2022/04-QAIP-Self-Assessment with Independent Validation 2021 | 2021-HQ-SAIV 2021 |  | Carles Soriano; Flora Moutard; Thiago de Oliveira Teodoro | 4-Finalization of Workpapers | Release |  | 2022-02-15 | 22.25 |  | 2021-11-16 |  |  | 2021-12-01 |  |  | 2022-02-10 |  |  | 2022-10-03 |  |  | 2022-02-15 |  | 1 | 243 | 5
2021 Audit Plan | IOS/AUD/2022/05-Remote audit of UNESCO's Office in Tehran | 2021-FO-TEH | Field Audit | Anastasia Beltyukova; Carles Soriano; Sameer Pise | 4-Finalization of Workpapers | Review Process |  | 2022-04-22 | 726 |  | 2022-01-14 | 12 |  | 2022-02-24 | 28 |  | 2022-04-22 | 22 |  | 2022-08-10 | 12 |  |  |  | 1 | 244 | 5
2022 Audit Plan | to delete | to delete |  | Ahmedou El Bah; Christian Muco; Flora Moutard |  |  |  |  | 0 | [15 empty] | 1 | 247 | 9
2022 Audit Plan | Audit of UNESCO's Cluster Office in San José (Remote) | 2022-FO-San Jose | Field Audit | Alicia Alvarez-Gracia; Carles Soriano; Flora Moutard; Oyuna Tumurbaatar; Tuyet-Mai Grabiel | 5-Follow-up of recommendations | Start follow-up | 2022-02-07 | 2022-07-11 | 792 |  | 2022-04-06 | 26 |  | 2022-05-31 | 40 |  | 2022-07-11 | 11 |  | 2022-08-04 | 3 |  |  |  | 1 | 248 | 9
2022 Audit Plan | Audit of UNESCO Regional Office in Yaoundé | 2022-FO-Yaounde | Field Audit | Carles Soriano; Flora Moutard; Helen Thanassoulias | 3-Reporting | Comments and Action Plans Received |  |  | 1061.75 |  | 2022-04-06 | 20 |  | 2022-04-06 | 40 |  |  | 16 |  | 2022-04-06 | 4 |  |  |  | 1 | 249 | 9
2022 Audit Plan | Review of UNESCO Staff Unions | 2022-HQ-Staff association |  | Anastasia Beltyukova; Carles Soriano; Flora Moutard; Sameer Pise | 5-Follow-up of recommendations | Closure of the last recommendation |  | 2022-04-14 | 216 |  | 2022-03-16 |  |  | 2022-03-31 |  |  | 2022-04-14 |  |  | 2022-06-01 |  |  |  |  | 1 | 251 | 9
2022 Audit Plan | 2022 Audit of UNESCO's Cybersecurity | 2022-IT-Cybersecurity |  | Christian Muco; Flora Moutard; Sameer Pise | 1-Planning | Notification Letter |  |  | 116.5 | [15 empty] | 1 | 278 | 9
2022 Audit Plan | Audit of the UNESCO Regional Office in Harare | 2022-FO-Harare | Field Audit | Anastasia Beltyukova; Carles Soriano; Sameer Pise | 2-Fieldwork | Exit Meeting |  | 2022-04-20 | 966.5 |  | 2022-08-04 |  |  | 2022-08-04 | [10 empty] | 1 | 281 | 9
2022 Audit Plan | Audit of UNESCO's Liaison Office in Addis Ababa | 2022-FO-Addis Ababa | Field Audit | Carles Soriano; Flora Moutard; Hir Purkait; Thiago de Oliveira Teodoro | 3-Reporting | Draft Report | 2022-04-29 |  | 431.75 |  | 2022-06-28 | 18 |  | 2022-08-04 | 45 |  | 2022-08-08 | 13 |  | 2022-09-06 | 4 |  |  |  | 1 | 282 | 9
2022 Audit Plan | Audit of UNESCO Internationa Institute for Capacity Building in Africa (IICBA) | 2022-IN-IICBA | Institute Audit | Carles Soriano; Flora Moutard; Hir Purkait; Thiago de Oliveira Teodoro | 4-Finalization of Workpapers | Review Process |  |  | 307.5 |  | 2022-04-29 | 31 |  | 2022-07-15 | 31 |  | 2022-07-22 | 31 |  |  | 17 |  |  |  | 1 | 283 | 9
2022 Audit Plan | Audit of the UNESCO Regional Office in Havana | 2022-FO-HAV | Field Audit | Alicia Alvarez-Gracia; Carles Soriano; Flora Moutard; Tuyet-Mai Grabiel | 2-Fieldwork | Exit Meeting |  |  | 684.5 |  | 2022-07-29 | 40 |  | 2022-09-02 | 50 |  |  | 20 |  |  | 5 |  |  |  | 1 | 284 | 9
2022 Audit Plan | Audit of Partnerships | 2022-HQ-Partnerships | HQ Audit | Alicia Alvarez-Gracia; Carles Soriano; Flora Moutard; Hir Purkait | 1-Planning | Notification Letter |  |  | 139.75 | [15 empty] | 1 | 285 | 9
2022 Audit Plan | Remote Audit of UNESCO's Office in Kinshasa | 2022-FO-Kinshasa Remote | Field Audit | Carles Soriano; Helen Thanassoulias; Thiago de Oliveira Teodoro | 1-Planning | Notification Letter |  |  | 132.5 | [15 empty] | 1 | 286 | 9
2022 Audit Plan | SC Certification of Financial Statement for RURITAGE EU project | 2022-HQ-SC RURITAGE EU project |  | Anastasia Beltyukova; Carles Soriano; Flora Moutard; Magda Ewelina Rembiesa; Sameer Pise | 2-Fieldwork | Interviews and Tests |  |  | 8 |  | 2022-09-29 | [13 empty] | 1 | 287 | 9
2022 Audit Plan | ICTP Certification of Financial Statement for ECPS EU project | 2022-ICTP-ECPS EU project |  | Anastasia Beltyukova; Carles Soriano; Flora Moutard; Magda Ewelina Rembiesa; Sameer Pise | 1-Planning | Notification Letter |  |  | 62 | [15 empty] | 1 | 288 | 9
2022 Audit Plan | Audit of the UNESCO Port-au-Prince Office | 2022-FO-POP | Field Audit | Anastasia Beltyukova; Carles Soriano; Tuyet-Mai Grabiel | 1-Planning | Notification Letter | 2022-09-16 |  | 11.5 | [15 empty] | 1 | 290 | 9
2022 Audit Plan | Audit of UNESCO's Office in Doha | 2022-FO-Doha | Field Audit | Carles Soriano; Christian Muco; Ivan Foo | 2-Fieldwork | Interviews and Tests |  |  | 1.5 | [15 empty] | 1 | 291 | 9
2022 Audit Plan | Audit of the UNESCO Tashkent Office | 2022-FO-TAS | Field Audit | Anastasia Beltyukova; Carles Soriano; Flora Moutard; Tuyet-Mai Grabiel | 1-Planning | Notification Letter |  | 2022-09-27 | 3 |  | 2022-09-27 | [13 empty] | 1 | 292 | 9